## Developer Summary
Team | Developer | Total Work Items | Completed Items | Items With Active Time | Sample Confidence % | Completion Rate % | On-Time Delivery % | Average Efficiency % | Average Delivery Score | Overall Developer Score | Total Active Hours | Total Estimated Hours | Avg Days Ahead/Behind | Reopened Items Handled | Reopened Rate % | Work Item Types | Projects Count | Early Deliveries | On-Time Deliveries | Late 1-3 Days | Late 4-7 Days | Late 8-14 Days | Late 15+ Days | Planned Hours Target | Estimation Discrepancy % | Estimation Reliability
Azure | jaime.reyes@inbest.cloud | 46 | 2 | 0 | 0 | 4.35 | 97.83 | 0 | 74.46 | 47.66 | 0 | 220.26 | -7.58 | 0 | 0 | 1 | 5 | 1 | 44 | 1 | 0 | 0 | 0 | 155 | 42.1 | Unreliable
SF-Nocedal | luis.nocedal@inbest.cloud | 44 | 37 | 0 | 0 | 84.09 | 31.82 | 0 | 77.5 | 54.55 | 0 | 159 | 6.52 | 0 | 0 | 1 | 3 | 5 | 9 | 5 | 8 | 11 | 6 | 155 | 2.6 | Good
SF-Nocedal | fernando.agredano@inbest.cloud | 40 | 39 | 34 | 85 | 97.5 | 22.5 | 56.99 | 93 | 77.62 | 124.9 | 172 | 1.49 | 0 | 0 | 1 | 3 | 4 | 5 | 16 | 15 | 0 | 0 | 155 | 11 | Good
QA | juan.catarina@inbest.cloud | 47 | 44 | 2 | 4.26 | 93.62 | 21.28 | 17.87 | 84.79 | 63.03 | 4.2 | 135.9 | 9.3 | 1 | 2.13 | 1 | 5 | 6 | 4 | 4 | 10 | 9 | 14 | 155 | -12.3 | Good
SF-Osvaldo | osvaldo.deluna@inbest.cloud | 56 | 55 | 4 | 7.14 | 98.21 | 7.14 | 19.24 | 89.55 | 65.03 | 6.83 | 104 | 5.63 | 0 | 0 | 1 | 6 | 0 | 4 | 5 | 38 | 6 | 3 | 155 | -32.9 | Review
QA | jonathan.bueno@inbest.cloud | 41 | 41 | 22 | 53.66 | 100 | 9.76 | 26.7 | 83.17 | 64.24 | 39.74 | 123.25 | 12.18 | 0 | 0 | 1 | 5 | 4 | 0 | 1 | 11 | 9 | 16 | 155 | -20.5 | Review
PMO | jair.alvarez@inbest.cloud | 96 | 53 | 14 | 14.58 | 55.21 | 65.62 | 12.38 | 65.26 | 50.57 | 7.67 | 220 | 5.43 | 0 | 0 | 1 | 5 | 17 | 46 | 4 | 17 | 1 | 11 | 155 | 41.9 | Unreliable
PMO | mayra.venegas@inbest.cloud | 89 | 86 | 0 | 0 | 96.63 | 7.87 | 0 | 80.45 | 55.51 | 0 | 142.18 | 13.74 | 2 | 2.25 | 1 | 7 | 3 | 4 | 10 | 9 | 23 | 40 | 155 | -8.3 | Good
SF-Erika | taurino.santiago@inbest.cloud | 49 | 47 | 0 | 0 | 95.92 | 24.49 | 0 | 86.02 | 59.85 | 0 | 176.67 | 6.26 | 0 | 0 | 1 | 7 | 3 | 9 | 1 | 15 | 16 | 5 | 155 | 14 | Good
Data | pablo.ruiz@inbest.cloud | 34 | 11 | 3 | 8.82 | 32.35 | 82.35 | 30.43 | 46.03 | 43.71 | 57.82 | 178 | 0.01 | 1 | 2.94 | 1 | 5 | 5 | 23 | 3 | 3 | 0 | 0 | 155 | 14.8 | Good
SF-Efrain | oswaldo.martinez@inbest.cloud | 25 | 25 | 18 | 72 | 100 | 0 | 22.83 | 82 | 61.71 | 34.98 | 158.27 | 10.1 | 1 | 4 | 1 | 3 | 0 | 0 | 4 | 7 | 4 | 10 | 155 | 2.1 | Good
QA | santiago.martinez@inbest.cloud | 13 | 3 | 0 | 0 | 23.08 | 76.92 | 0 | 45 | 33.65 | 0 | 27.5 | 0.69 | 0 | 0 | 1 | 4 | 0 | 10 | 3 | 0 | 0 | 0 | 155 | -82.3 | Unreliable
SF-Alejandro | uriel.cortes@inbest.cloud | 67 | 64 | 10 | 14.93 | 95.52 | 7.46 | 27.12 | 80.45 | 62.08 | 52.2 | 143.75 | 11.11 | 1 | 1.49 | 1 | 4 | 2 | 3 | 0 | 24 | 16 | 22 | 155 | -7.3 | Good
SF-Alejandro | gerardo.melgoza@inbest.cloud | 61 | 61 | 32 | 54.24 | 100 | 8.47 | 26.2 | 88.22 | 66.51 | 59 | 129.1 | 6.99 | 0 | 0 | 1 | 5 | 0 | 5 | 11 | 23 | 13 | 7 | 155 | -16.7 | Review
SF-Erika | prisciliano.aquino@inbest.cloud | 53 | 53 | 18 | 33.96 | 100 | 32.08 | 19.85 | 95 | 70.67 | 8.39 | 163.5 | 2.28 | 1 | 1.89 | 1 | 6 | 5 | 12 | 19 | 11 | 5 | 1 | 155 | 5.5 | Good
Obok | samuel.vazquez@inbest.cloud | 7 | 5 | 5 | 71.43 | 71.43 | 28.57 | 32.45 | 67.86 | 55.61 | 10.8 | 18 | 18.34 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 4 | 155 | -88.4 | Unreliable
Obok | luis.martinez@inbest.cloud | 4 | 2 | 2 | 50 | 50 | 50 | 57.78 | 66.25 | 60.07 | 7.2 | 15 | 7.22 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 1 | 155 | -90.3 | Unreliable
Data Center | fernando.valdovinos@inbest.cloud | 10 | 8 | 0 | 0 | 80 | 20 | 0 | 78.5 | 53.25 | 0 | 71.4 | 6.54 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 5 | 0 | 2 | 155 | -53.9 | Unreliable
Azure | luis.aquino@inbest.cloud | 15 | 0 | 0 | 0 | 0 | 100 | 0 | 66.67 | 43.33 | 0 | 159.99 | 0 | 0 | 0 | 1 | 3 | 0 | 15 | 0 | 0 | 0 | 0 | 155 | 3.2 | Good
SF-Efrain | jared.marquez@inbest.cloud | 36 | 33 | 3 | 8.57 | 91.67 | 11.43 | 7.25 | 78.71 | 56.06 | 4.92 | 152.5 | 10.22 | 0 | 0 | 1 | 7 | 0 | 4 | 3 | 8 | 10 | 10 | 155 | -1.6 | Good
Lider | fernando.hernandez@inbest.cloud | 3 | 0 | 0 | 0 | 0 | 100 | 0 | 66.67 | 43.33 | 0 | 25 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 155 | -83.9 | Unreliable
SF-Hans | hans.izarraraz@inbest.cloud | 49 | 10 | 8 | 16.33 | 20.41 | 81.63 | 3.62 | 24.69 | 24.48 | 0.89 | 148.5 | 1.17 | 1 | 2.04 | 1 | 5 | 1 | 39 | 0 | 6 | 2 | 1 | 155 | -4.2 | Good
Cybersecurity | ricardo.martinez@inbest.cloud | 16 | 12 | 8 | 50 | 75 | 43.75 | 22.22 | 82.5 | 62.43 | 9.72 | 83 | 16.57 | 1 | 6.25 | 1 | 3 | 3 | 4 | 1 | 1 | 1 | 6 | 155 | -46.5 | Unreliable
UX/UI | ximena.segura@inbest.cloud | 13 | 11 | 7 | 53.85 | 84.62 | 23.08 | 71.41 | 87.69 | 76.7 | 39.29 | 53.04 | 1.88 | 0 | 0 | 1 | 6 | 1 | 2 | 5 | 4 | 1 | 0 | 155 | -65.8 | Unreliable
SF-Hans | fernando.alcaraz@inbest.cloud | 48 | 44 | 28 | 58.33 | 91.67 | 68.75 | 124 | 94.79 | 99.02 | 83.12 | 126.93 | -0.46 | 0 | 0 | 1 | 4 | 23 | 10 | 12 | 3 | 0 | 0 | 155 | -18.1 | Review
PMO | jesus.hernandez@inbest.cloud | 5 | 1 | 0 | 0 | 20 | 100 | 0 | 46 | 36 | 0 | 190.33 | -3.66 | 0 | 0 | 1 | 2 | 1 | 4 | 0 | 0 | 0 | 0 | 155 | 22.8 | Review
Obok | fredy.osorio@inbest.cloud | 8 | 6 | 6 | 75 | 75 | 37.5 | 92.54 | 76.25 | 76.26 | 53.6 | 53.67 | 5.22 | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 0 | 0 | 3 | 155 | -65.4 | Unreliable
Obok | eyden.villanueva@inbest.cloud | 7 | 4 | 4 | 57.14 | 57.14 | 42.86 | 99.97 | 79.29 | 77.49 | 29.88 | 41.83 | 2.53 | 0 | 0 | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 1 | 155 | -73 | Unreliable
R&D | oscar.gallo@inbest.cloud | 9 | 8 | 6 | 66.67 | 88.89 | 11.11 | 75.52 | 80 | 73.33 | 90.07 | 190 | 13.63 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 4 | 4 | 155 | 22.6 | Review
PMO | juan.martinez@inbest.cloud | 49 | 23 | 0 | 0 | 46.94 | 61.22 | 0 | 68.37 | 47.35 | 0 | 175 | 5.32 | 0 | 0 | 1 | 6 | 3 | 27 | 0 | 6 | 5 | 8 | 155 | 12.9 | Good
PMO | veronica.medrano@inbest.cloud | 12 | 9 | 0 | 0 | 75 | 41.67 | 0 | 95 | 62.92 | 0 | 50 | 1.98 | 1 | 8.33 | 1 | 1 | 0 | 5 | 4 | 2 | 1 | 0 | 155 | -67.7 | Unreliable
Obok | gerardo.barcenas@inbest.cloud | 4 | 3 | 2 | 50 | 75 | 25 | 86.25 | 96.25 | 83.44 | 7.2 | 17 | 1.52 | 0 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 0 | 0 | 155 | -89 | Unreliable